## Home
Zero Trust Assessment for …
Assessed on: 24 Mar 2024
Threat intelligence
Organization policy
Identity
Device
Infrastructure
Network
Threat protection
Multi-factor authentication
User/session risk
Data
Apps
Classify, label, encrypt
Device risk state
Device inventory
Adaptive access
Access and runtime control
Security policy enforcement
Real-time policy evaluation
Visibility and Analytics
Automation
Not Deployed
Partially deployed
Fully deployed
aka.ms/ztassess
Not evaluated
<TenantName>

## Identity ✍️
Identity Zero Trust Roadmap | [8 empty] | Legend | ☉ Not started | ✜ In planning | ✜ Planned | ▷ In progress | ✓ Completed | ⦿ Blocked | ✢ First Party other | ※ Third Party | ✕ Will not pursue | ⚐ MS Roadmap | ⚐ Follow up
Workshop date →
| Design Conditional Access posture | Rollout CA with MFA controls | Rollout CA with device controls | Rollout CA with risk controls | Rollout CA for External Identities
| ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
| Stop buying or building Active Directory dependent apps | Migrate VPN auth to Azure AD | Enable on-prem remote access for web apps without VPN | Rollout governance for app assignments
| ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
| Disover and triage modern apps | Define app infra server mgmt strategy | Deploy Azure AD Domain Services | Remove app infra servers from AD | Define and rollout VDI strategy | Migrate print servers to cloud
| ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
Decommission on-prem federation servers
☉ Not started
| Disover and triage legacy apps | Migrate SSO for employee federated apps | Migrate SSO for employee WAM apps | Decommission WAM servers | Migrate SSO for External Identities federated apps | Migrate SSO for external ids (WAM & others)
| ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
| Stop issuing on-prem accounts for new external users | Migrate on-prem external ids & workflows to Azure AD External ID | Decommission on-prem external user systems | Rollout governance for External IDs |  |  | Enable user writeback | Change provisioning flow of existing users to AAD
| ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started |  |  | ⚐ MS Roadmap | ⚐ MS Roadmap
| Start provisioning cloud apps via Azure AD app provisioning | Migrate existing SaaS app provisioning to Azure AD | Migrate HR provisioning flow to Azure AD | Migrate joiner/mover/leaver workflows to Azure AD | Migrate existing on-prem app provisioning to Azure AD |  | Decommission on-prem IDM system
| ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started |  | ⚐ MS Roadmap
|  | Rollout Authenticator App (MFA, SSPR, Passwordless) | Migrate on-prem MFA systems | Migrate self-service password reset | Develop credential (incl. Passwordless) strategy | Deploy Password Protection
|  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
|  | Turn on Password Hash Sync | Migrate to Password Hash Sync auth
|  | ☉ Not started | ☉ Not started
|  | Rollout Windows Hello for Business | Rollout FIDO2 | Rollout Authenticator Passwordless | Drive passwordless usage |  | Remove password as credential
|  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started |  | ⚐ MS Roadmap
|  | Migrate to modern tools for collab (OneDrive, Teams, SharePoint) | Migrate distributions lists to Microsoft 365 Teams & Groups
|  | ☉ Not started | ☉ Not started
|  | Use cloud groups for new cloud app authorization | Enable group writeback | Rollout governance for groups | Migrate group management workflows |  | Change provisioning flow of existing groups to AAD
|  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started |  | ⚐ MS Roadmap
| Deploy Hybrid Azure AD Join | Define Azure AD Join strategy | Rollout Azure AD Join for new workstations | Rollout AutoPilot | Remove DJ Windows clients from Active Directory
| ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
|  | Deploy macOS mgmt with Intune / JAMF | Deploy macOS SSO Extension
|  | ☉ Not started | ☉ Not started
| Define policy & use least privileged roles | Discover existing privileged roles | Discover & remediate existing overprivileged accounts
| ☉ Not started | ☉ Not started | ☉ Not started
| Use cloud-only privileged accounts | Rollout Access Reviews for cloud privileged accounts & groups | Plan privileged accounts lifecycle (JML)
| ☉ Not started | ☉ Not started | ☉ Not started
| Rollout PIM for Tier-Zero roles | Rollout PIM for remaining roles
| ☉ Not started | ☉ Not started
| Discover & remediate existing overprivileged Workload Identities | Discover & analyze privileged usage for Workfload Identities (eg scripts) | Rollout strong auth credentials for Workload Identities | Rollout Conditional Access for Workload Identities | Enforce authentication with strong creds for all privileged accounts
| ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
Deploy Cloud Privileged Access Workstations
☉ Not started
| Lock down Azure AD tenant config | Integrate all Azure AD logs into SIEM | Develop security playbooks based on Azure AD logs | Remediate risk signals from Identity Protection & MDI
| ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
|  | Implement monitoring for Azure AD Connect | Remediate Azure AD connect Health alerts | Implement monitoring for hybrid connectors
|  | ☉ Not started | ☉ Not started | ☉ Not started
Apps
First
Next
Access
Passwordless
Then
Windows
Infrastructure
Authentication
Provisioning
Users
&
Groups
Hybrid
Groups
Devices
macOS
Operations
Privilege
Just-In-Time
Credentials
PAW
SecOps
<TenantName>
aka.ms/ztassess
<TenantName>
<TenantID>
Note on G14: Establish the high level security posture of the organization. This will drive how the conditional access policies should look like.
Note on L14: Rollout Conditional Access policies to protect your apps with MFA
Note on N14: Update your CA policies to allow access from compliant device, or hybrid ad join
Note on P14: Update your CA policies to include additional controls for based on user and sign-in risk
Note on R14: Deploy cross-tenant access policies, and create dedicated conditional access policies targeting external users
Note on G17: New applications procured or built by the organization use modern authentication protocols and use Azure AD as the identity provider.
Note on L17: Configure your VPN infrastructure to use Azure AD for SSO.
Note on N17: Deploy AppProxy and/or SHA
Note on P17: Define Access Reviews for application assignments and for underlying security group
Note on G20: Identify all the modern auth applications that are not in Azure AD and migrate to Azure AD. This includes apps based on SAML, WS-Federation, Oauth, or Open ID Connect across the existing systems (ADFS, or similar on prem or cloud IDPs) that will be migrated to Azure AD
Note on L20: Define approach to set policies, updates, configuration, monitoring to servers, that does not rely on AD/on-premises
Note on N20: Enable Azure AD Domain Services to prepare the migration of servers that are currently joined to on-premises infrastructure
Note on P20: Move servers in your on-premises domain to either Azure AD Domain Services, or virtualized domain controllers in IaaS
Note on R20: Define approach to VDI to either adopt a cloud-managed solution like Windows 365 or Azure Virtual Desktop, or integrate existing solution with Azure AD for SSO
Note on T20: Deploy cloud-first print services such as Universal Print
Note on L23: Switch federated domains to use Azure AD managed authentication, turn off federation servers, and clean up infrastructure and directory
Note on G26: Identify all the applications in the environment that use Integrated Windows Authentication, LDAP, Kerberos, or similar legacy protocols
Note on L26: Migrate SSO configuration of applications for employees from on-premises IDPs like ADFS to Azure AD
Note on N26: Migrate SSO configuration of applications for employees from on-premises WAM solutions like CA Siteminder to Azure AD
Note on P26: Switch federated domains to use Azure AD managed authentication, turn off WAM servers, and clean up infrastructure and directory.
Note on R26: Migrate SSO configuration of applications for external identities (contractors, partners, vendors, etc.) from on-premises IDPs like ADFS to Azure AD
Note on T26: Migrate SSO configuration of applications for external identities (contractors, partners, vendors, etc.) from on-premises WAM Solutions like CA Siteminder to Azure AD
Note on G30: Use Azure AD B2B for new external Identities
Note on L30: Use Azure AD External Identities for guest identities and workflows
Note on N30: Stop using on-prem external user systems and use Azure AD instead
Note on P30: Deploy Azure AD governance features(such as Entitlement Management and Access Reviews) for external Identities
Note on X30: Not supported currently. This is the ability to create a user in Azure AD and writeback to on-prem
Note on Z30: Not supported currently. For the onprem users, switch their source of authority to Azure AD
Note on G33: For new cloud applications, provision them via Azure AD
Note on L33: Migrate exisiting SaaS application provisioning to Application Provisioning
Note on N33: Migrate an existing Cloud HR provision to Azure AD provisioning
Note on P33: Migrate joiners/movers/leavers workflows
Note on R33: Migrate to Azure AD Application provisioning
Note on X33: Not currently supported. Decommission the on-prem IDM system and use Azure AD
Note on L36: Deploy Authenticator App in your organization for SSPR, MFA and Passwordless Phone sign-in
Note on N36: Migrate from a federated MFA to Azure MFA
Note on P36: Migrate from on-prem SSPR to Azure AD SSPR
Note on R36: Create password complexity,length, or age in Azure AD
Note on T36: Deploy Password Protection to block known weak passwords(global) and additional weak terms specific to your organization(custom)
Note on L39: Turn on Password Hash sync as backup for your federated environment
Note on N39: Move from federated to a Managed Authentication (Password Hash Sync) method
Note on L42: Deploy Windows Hello For Business for users in the Organization
Note on N42: Deploy FIDO2 keys to users in the organization
Note on P42: Enable authentication type so that users can start using Passwordless Phone Sign in
Note on X42: Not currently supported. Remove the ability for users to log in with a password/ Enforce passwordless
Note on L45: Roll out modern applications like SPO, OD4B, Yammer etc. for collaboration
Note on N45: Migrate existing Distribution lists to M365 groups
Note on L48: Assign Azure AD security groups to new cloud applications
Note on N48: Enable the ability to write cloud groups to your on-premises AD instance
Note on P48: Enable Access Reviews and/or Entitlement Management Packages
Note on R48: Group CRUD and membership management operation workflows
Note on X48: Not supported currently. For the onprem groups, switch their source of authority to Azure AD
Note on G52: Configure Hybrid Azure AD join for the existing Domain Joined Windows
Note on L52: Learn and develop a strategy to go AADJ for new Windows devices
Note on N52: Use AADJ for new Windows clients setup
Note on P52: Use Autopilot for device provisioning
Note on R52: Migrate DJ/HAADJ devices to AADJ if/when tool is provided from Microsoft
Note on L55: Manage MacOS with Intune, integrate Jamf if used
Note on N55: Deploy Enterprise SSO plug-in for Apple devices
Note on G59: For new privileged roles request, assign the least privileged role
Note on L59: Create an inventory that outlines who in the organization has privileged roles
Note on N59: Based on business requirements, re-assign users with excessive permissions to least privileged roles
Note on G62: Use cloud-only accounts for privileged roles in the cloud
Note on L62: Rollout periodic access reviews for privileged users and groups
Note on N62: Define the approach to create, update, delete privileged accounts
Note on G65: Enable JIT activation of privileged roles for the most critical roles such as Global Administrator
Note on L65: Enable JIT activation of privileged roles for remaining role assignments
Note on G68: Based on business requirements, re-assign workload identities/system acccounts with excessive permissions to least privileged roles
Note on L68: Create an inventory of non-human identities (e.g. service accounts, or accounts that run scripts or scheduled tasks)
Note on N68: Use Azure Managed Identities, certificates for cloud workload identities
Note on P68: Define conditional access policies that target workload identities
Note on R68: Rollout strong authentication methods for all privileged accounts and enforce the authentication using those methods
Note on L71: Design procurement procedures and security controls for privileged access workstations for all management activities
Note on G74: Review the configuration of Azure AD tenant and lock down settings per business needs and MS best practices
Note on L74: Ingest all data signal from Azure AD to SIEM systems
Note on N74: Define procedures to detect, respond and remediate incidents based on log activity
Note on P74: Triage and address initial risk signals generated by Mirosoft Defender for Identity and Azure AD Identity protection. Then, incorporate these signals into secops playbooks
Note on L77: Deploy Azure AD Connect Health for monitoring of Azure AD Connect and ADFS
Note on N77: Triage and address findings for Azure AD Connect Health
Note on P77: Monitor all hybrid agents deployed on premises. This will be a combination of cloud signal, and event logs on the servers where the agents are deployed

## Device ✍️
Devices Zero Trust Roadmap | [8 empty] | Legend | ☉ Not started | ✜ In planning | ✜ Planned | ▷ In progress | ✓ Completed | ⦿ Blocked | ✢ First Party other | ※ Third Party | ✕ Will not pursue | ⚐ MS Roadmap | ⚐ Follow up
Workshop date →
|  | Filters | Device groups | User groups | Scope Tags | Scope Groups | Offboarding Strategy | Connectors
|  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
|  | Organizational Messages | Log Analytics | Data Warehouse | Graph API | Multi-Admin Approval | AI | Quiet Time
|  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
[7 empty] | Automation / Orchestration | DEX
[7 empty] | ☉ Not started | ☉ Not started
| Review enrolled vs unenrolled for BYOD/Corporate |  | Data protection | Access requirements | Conditional launch
| ☉ Not started |  | ☉ Not started | ☉ Not started | ☉ Not started
| Review security, compliance, resource access requirements (Certs/Wi-Fi/VPN) |  | Backup to iCloud | 3rd Party Keyboard
| ☉ Not started |  | ☉ Not started | ☉ Not started
|  |  | Data protection framework using App protection | MAM Compliance and Conditional Access | RBAC | Remote actions
|  |  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
| Review App config vs App protection policies |  | App config settings | Managed Edge Browser | Mobile Threat Defense
| ☉ Not started |  | ☉ Not started | ☉ Not started | ☉ Not started
| Review enrolled vs unenrolled for BYOD/Corporate |  | Data protection | Access requirements | Conditional launch
| ☉ Not started |  | ☉ Not started | ☉ Not started | ☉ Not started
| Review security, compliance, resource access requirements (Certs/Wi-Fi/VPN) |  | Device Manufacturers | Screen capture and Google Assistant | Approved keyboards | Require device lock
| ☉ Not started |  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
|  |  | Knox Attestation | Require SafetyNet | SafetyNet/ Hardware Back Key
|  |  | ☉ Not started | ☉ Not started | ☉ Not started
|  |  | Data protection framework using App protection | MAM Compliance and Conditional Access | RBAC | Remote actions
|  |  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
| Review App config vs App protection policies | App config settings | Managed Edge Browser | Mobile Threat Defense |  |  | Require Threat Scan on apps
| ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started |  |  | ☉ Not started
| Review enrolled vs unenrolled for BYOD/Corporate |  | Compliance policy | Conditional access policy | Enrollment Restrictions |  | Mobile Threat Defense
| ☉ Not started |  | ☉ Not started | ☉ Not started | ☉ Not started |  | ☉ Not started
| Review security, compliance, resource access requirements (Certs/Wi-Fi/VPN) |  | Certificates | VPN | Wi-Fi | iOS Updates
| ☉ Not started |  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
| Review provisioning strategy |  | Store app deployment | LoB app Deployment | VPP app deployment | Webapp Deployment
| ☉ Not started |  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
| APNS Certificate |  | User enrollment | ABM Provisioning
| ☉ Not started |  | ☉ Not started | ☉ Not started
| Apple Managed Accounts |  | RBAC | Remote actions
| ☉ Not started |  | ☉ Not started | ☉ Not started
| FLW / Shared Devices |  | Entra Shared Device Mode | Shared iPad
| ☉ Not started |  | ☉ Not started | ☉ Not started
|  |  | App config settings | VPN tunnel | Tunnel based VPN access for enrolled devices |  | Remote Assistance
|  |  | ☉ Not started | ☉ Not started | ☉ Not started |  | ☉ Not started
| Review enrolled vs unenrolled for BYOD/Corporate |  | Compliance policy | Conditional access policy | Enrollment Restrictions |  | Mobile Threat Defense
| ☉ Not started |  | ☉ Not started | ☉ Not started | ☉ Not started |  | ☉ Not started
| Review security, compliance, resource access requirements (Certs/Wi-Fi/VPN) |  | Certificates | VPN | Wi-Fi |  | Tunnel based VPN access for enrolled devices
| ☉ Not started |  | ☉ Not started | ☉ Not started | ☉ Not started |  | ☉ Not started
| Review app provisioning strategy |  | Store app deployment | LoB app Deployment | Web app deployment
| ☉ Not started |  | ☉ Not started | ☉ Not started | ☉ Not started
| Android Device Administrator Retirement |  | User enrollment | Userless Enrollment | Android Enterprise | Kiosk Devices | AOSP | Teams Devices
| ☉ Not started |  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
| Offboarding Devices |  | RBAC | Remote actions | Remote Log Collection
| ☉ Not started |  | ☉ Not started | ☉ Not started | ☉ Not started
| FLW / Shared Devices |  | Managed Home Screen | Entra Shared Device Mode
| ☉ Not started |  | ☉ Not started | ☉ Not started
|  |  | App config settings | Zebra FOTA | Samsung FOTA | AR / VR Devices | Remote Assist
|  |  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
| Review provisioning strategy | Deploy Hybrid Entra Join (HEJ/HAADJ) | Deploy Entra Join Only (EJ/AADJ) | Stop AD DJ for new workstations | Autopilot User Enrollment | Autopilot Pre-provisioning
| ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
|  | Migrate GPO to MDM policies | GP Preferences | File Shares to Cloud | Apps Delivery / App Compat | WSUS to WUFB
|  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
| Co-management Strategy | Compliance Policies | Device Configuration | Office Apps | Client Apps | Windows Update
| ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
|  | MDM based policies for certs | MDM based policies for Wi-Fi | MDM based policies for VPN | Browser | VDI Strategy | Cloud PKI | MAM for Edge
|  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
|  | Enrollment Restrictions | Compliance Policy | Disk Encryption (Bitlocker) | Security Baselines | Cloud LAPS | Custom Compliance Policies | EPM
|  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
|  | Update Rings | Security Updates | Quality Updates | Delivery Optimization |  | Windows 11
|  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started |  | ☉ Not started
|  | Office Apps via Intune | Store Apps | LOB Apps via Intune | WDAC / App Control | WIP for Enrolled | Policies for Office Apps
|  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
|  | Endpoint Analytics | Proactive Remediations | Organizational messages | Remote Assistance | Unattended Remote Assistance | Scripts | Remote Log Collection
|  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
|  | Desktop Analytics | WIP for Unenrolled
|  | ☉ Not started | ☉ Not started
|  | Deploy MDM based policies for EDR/AV | MDM based policies for security baselines | MDM based policies for BitLocker | MDM based policies for firewall
|  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
|  | Attack surface reduction | Account protection
|  | ☉ Not started | ☉ Not started
| Review current management needs | AMB provisioning | Device config policies through settings catalog | Deploy macOS SSO extension | AV/EDR | Firewall | Local account management
| ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
| Evaluate macOS management with Intune + JAMF | Deploy MDM based policies for EDR/AV | Certificates / Wi-Fi / VPN | App management | Remote actions | FileVault encryption | Native update management
| ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
Remote Assist
☉ Not started
Tenant Administration
MAM
App Protection
for
iOS devices
First
Next
Foundational requirements
Advanced reqs
MAM
App Protection
for
Android devices
Foundational requirements
Advanced reqs
Then
MDM
iOS & iPadOS devices
Foundational requirements
Setup App Protection
Device config profiles
Enrollment
App deployment
Grouping & targeting
Advanced requirements
MDM
Android devices
Foundational requirements
Compliance & CA
Device config policies
Enrollment
App deployment
Grouping & targeting
Advanced requirements
MDM
Windows devices
EndPoint Security
MDM
macOS devices
Foundational requirements
Compliance & CA
Android Only Settings
Android Only Settings
FLW/Shared Device
FLW/Shared Device
Windows Enrollment
Path to Microsoft Entra Join
Resource Access
Security
Windows Updates
Windows Apps
Misc. Windows
Windows Legacy
Co-Management
Setup App Protection
iOS Only Settings
<TenantName>
aka.ms/ztassess

## Dev SecOps ✍️
Dev SecOps Roadmap | [8 empty] | Legend | ☉ Not started | ✜ In planning | ✜ Planned | ▷ In progress | ✓ Completed | ⦿ Blocked | ✢ First Party other | ※ Third Party | ✕ Will not pursue | ⚐ MS Roadmap | ⚐ Follow up
Workshop date →
| Design permissions and access | Discover servers/infra for build/deploy code | Harden servers/infra for build/deploy code | Define Developer Workstation Policies | Implement Defender for Servers to continuously monitor | Harden target infra (Defender for Cloud)​
| ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
|  | Define developer access policies using Access Packages | Implement access and PIM (JIT/JEA) policies for developers | Define Governance Approach for Groups with DevSecOps priveleges​
|  | ☉ Not started | ☉ Not started | ☉ Not started
|  | Discover existing GitHub Accounts and permissions | Integrate GitHub with Entra ID​ | Remediate non-Entra ID accounts and assignments​ | Discover, review and adjust permissions based on role​ |  | Create process to periodically review unused/stale credentials​
|  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started |  | ☉ Not started
|  | Design code publishing approach | Configure publishing approach for deploying to Azure​ | Define developer access to Azure as needed​
|  | ☉ Not started | ☉ Not started | ☉ Not started
|  | Design organization security and analysis settings​ | Decide if default or advanced custom setup for CodeQL​ | Deploy Github Advanced Security - CodeQL​ | Deploy Github Secret Scanning​ | Specify configuration settings for Dependabot​ | Integrate with Defender for DevOps​ | Triage results and remediate​
|  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
|  | Deploy GitHub Advanced Security - Dependabot​ | Evaluate SAST and DAST tools (3P)​
|  | ☉ Not started | ☉ Not started
|  | Discover existing ADO accounts and permissions ​ | Remediate non-Entra ID accounts and assignments​ | Integrate Entra ID to ADO​ | Discover, review and adjust permissions based on role​ | Set up Service Connections to deploy to Azure ​
|  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
|  | Design code publishing approach​ | Configure publishing approach for deploying to Azure​
|  | ☉ Not started | ☉ Not started
|  | Deploy GitHub Advanced Security for Azure DevOps​ | Integrate with Defender for DevOps​ | Triage results and remediate​ | Evaluate Dynamic Scanning (3P)​
|  | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started
Foundation
First
Next
Azure DevOps
Then
<TenantName>
aka.ms/ztassess
Infrastructure
Identities
Identity and Access
CI/CD Pipeline
GitHub
Scanning
Scanning
Identity and Access
CI/CD Pipeline
Scanning

## Data ✍️
Data Roadmap | [8 empty] | Legend | ☉ Not started | ✜ In planning | ✜ Planned | ▷ In progress | ✓ Completed | ⦿ Blocked | ✢ First Party other | ※ Third Party | ✕ Will not pursue | ⚐ MS Roadmap | ⚐ Follow up
Workshop date →
| Monitor sharing confidential information with external partners | Monitor sharing confidential information with customers | Use information protection mechanisms (e.g. encryption, DLP, etc.) | Use data governance mechanisms (e.g. retention policies, archiving, etc.) | Ensure all known means of sharing data (or illicit exfiltration of data) are understood, approved, and documented |  | Define SharePoint Permission Strategy | Identify use cases for special cryptography needs. E.g. Azure Information Protection - Bring you Own Key
| ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started | ☉ Not started |  | ☉ Not started | ☉ Not started
| Manage Alerts and incidents for information protection and data loss prevention | Identify and classify data and apply controls based on the importance to the business | Identify use cases for automatic labeling (based on SITs) |  | Identify and classify sensitive assets
| ☉ Not started | ☉ Not started | ☉ Not started |  | ☉ Not started
Establish minimum standards for trusted devices and accounts that access any data assets belonging to the organization
☉ Not started
[5 empty] | Plan for the protection of High Value Assets | Plan for the protection of High Value Assets | Plan for the protection of High Value Assets
[5 empty] | ☉ Not started | ☉ Not started | ☉ Not started
Then
Identify, classify & protect sensitive data
First
Next
<TenantName>
aka.ms/ztassess
Use least privilege access
Access
Set minimum standards for data access
Use least privilege access
Protect High Value sensitive data
Use least privilege access

## Identity ⚙️
Workload identity: Conditional access policies
Conditional access policy name | State | Policy Json
Azure Active Directory Tenant Configuration
Conditional Access for workload identities enables blocking service principals from outside of trusted public IP ranges, or based on risk detected by Azure AD Identity Protection.
<TenantName>
aka.ms/ztassess

## Device ⚙️
Windows automatic enrollment
Type | Name |  |  | User scope | Group
Enrollment device platform restrictions
Platform |  | Priority | Name |  | MDM | Min Ver | Max Ver | Personally owned |  | Blocked manuf. | Scope | Assigned to
Compliance policies
Platform |  | Policy name |  |  | Defender for EndPoint | Min OS version | Max OS version | Require pswd | Min pswd length | Password type | Pswd expiry (days) | Count of previous pswds to block | Max inactivity (min) | Require encryption | Rooted / Jailbroken devices | Max Device Threat Level | Require Firewall | Action for noncompliance (days) Push notification |  | Action for noncompliance (days) Send email |  | Action for noncompliance (days) Remote lock |  | Action for noncompliance (days) Block |  | Action for noncompliance (days) Retire |  | Scope |  | Included groups |  | Excluded groups
App protection policies
[5 empty] | Apps |  |  |  | Data protection | [15 empty] | Conditional launch - App conditions | [5 empty] | Conditional launch - Device conditions |  |  |  |  | Assignments
Platform |  | Policy name |  |  | Public apps |  | Custom apps |  | Backup org data to iCloud or Google | Send org data to other apps | Apps to exempt | Save copies of org data | Allow user to save copies to selected services | Transfer telecommunication data to | Receive data from other apps | Open data into Org documents | Allow users to open data from selected services | Restrict cut, copy, and paste between other apps | Cut and copy character limit for any app | Encrypt org data | Sync policy managed app data with native apps or add-ins | Printing org data | Restrict web content transfer with other apps | Org data notifications | Max PIN attempts (Action) |  | Offline grace period Block access (min) | Offline grace period Wipe data (days) | Disabed account | Min app version (Action) | Rooted / Jailbroken devices | Primary MTD service | Max allowed device threat level | Min OS version | Max OS version | Scope | Included groups | Excluded groups
Configure Windows devices to enroll when they join or register with Azure Active Directory. We recommend setting this to all instead of selected groups and using enrollment restrictions to configure the intake of users.
Device enrollment restrictions let you restrict devices from enrolling in Intune based on certain device attributes. Device platform restrictions restrict devices based on device platform, version, manufacturer, or ownership type.
Device enrollment restrictions let you restrict devices from enrolling in Intune based on certain device attributes. Device platform restrictions restrict devices based on device platform, version, manufacturer, or ownership type.
App protection policies (APP) are rules that ensure an organization's data remains safe or contained in a managed app. A policy can be a rule that is enforced when the user attempts to access or move "corporate" data, or a set of actions that are prohibited or monitored when the user is inside the app. A managed app is an app that has app protection policies applied to it, and can be managed by Intune.
Intune Tenant Configuration
<TenantName>
aka.ms/ztassess
Note on U28: Max minutes of inactivity before password is required

## Identity ☑️
[6 empty] | Legend | ☉ Not started | ✜ Planned | ▷ In progress | ✓ Completed | ⦿ Blocked | ※ Third Party | ✕ Will not pursue | ⚐ MS Roadmap
[7 empty] | ☉ Not started (P0) | ☉ Not started (P1) | ☉ Not started (P2)
Assessment check |  | Result |  | User impact | Risk level
Workload identities
| 🚦 |  | Configure conditional access policies for workload identities | Low | Moderate
|  |  | Workload identities authentication methods | Moderate | Moderate
Privileged identities
|  |  | Configure JIT access for privileged roles | High | High
|  |  | Conditional Access require phishing resistent credentials for privileged users | High | High
|  |  | Cloud-Only Accounts hold cloud privileged roles | Moderate | High
User identities
|  |  | Usage of authentication strengths for all users | High | Moderate
|  |  | Secure registration of security info | Moderate | High
|  |  | Enable phishing resistant authentication methods | Moderate | Moderate
|  |  | Configure a registration campaign to set up Microsoft Authenticator app | Moderate | Moderate
|  |  | Use of recommended authentication methods for users | Moderate | Moderate
|  |  | Require strong authentication for non-privileged users | High | High
|  |  | Enable Password Protection for on-premises accounts | Moderate | Medium
|  |  | Enable custom list of banned passwords | Moderate | Medium
Device and app (MAM) compliance
|  |  | Mobile Application Management enforcement | Moderate | Moderate
|  |  | Compliant device enforcement | High | Moderate
Identity Zero Trust Assessment
Configure CA policies for workload identities
Protect your workload identities (service principals and Managed Identities) by creating policies to protect based on risk and location
P1: Missing CA policies for service principals
Threats: Elevation of Privilege
Remediation: Configure Conditional Access Policies for service principals
Remediation impact: This change will have low impact on your users.
Learn more: Azure Active Directory Conditional Access for workload identities
Workload identities authentication methods
Privileged Identity Management provides time-based and approval-based role activation to mitigate the risks of excessive, unnecessary, or misused access permissions.
P1: Missing authentication method policy for service principal or it allows client secret.
Threats: Elevation of Privilege
Remediation: Configure Conditional Access Policies for service principals
Remediation impact: This change will have low impact on your users.
Learn more: Azure AD application authentication methods API overview - Microsoft Graph v1.0
Score
-%
Configure JIT access for privileged roles
Privileged Identity Management provides time-based and approval-based role activation to mitigate the risks of excessive, unnecessary, or misused access permissions.
P0: Privileged Identity Management just-in-time activation policies are not enabled for all Global Administrators.
Threats: Elevation of Privilege
Remediation: Configure PIM to enable JIT activation policies for privileged roles
Remediation impact: Medium. Requires comms and alignment within privileged users
Learn more: Configure Azure AD role settings in PIM
Conditional Access require phishing resistent credentials for privileged users
Microsoft recommends using phishing-resistant credentials for privileged roles.
P1: Customer has NOT deployed a CA Policy for Global Administrators that require phishing-resistant credentials.
Threats: Phishing
Remediation: Configure Conditional Access Policies for privileged users requiring phishing-resistant authentication strength.
Remediation impact: This change will have a moderate impact on your users.
Learn more: Overview of Azure Active Directory authentication strength
Cloud-Only Accounts hold cloud privileged roles
No on-premises accounts should have administrative privileges in Microsoft 365.
P0: Sync accounts have Global Admin role
Threats: Lateral Movement, privilege escalation
Remediation: Provision new privileged accounts and re-assign roles
Remediation impact: High. Need to re-provision and re-assign permissions
Learn more: Assign Azure AD roles to users
Usage of authentication strengths for all users
No on-premises accounts should have administrative privileges in Microsoft 365.
P0: Sync accounts have Global Admin role
Threats: Lateral Movement, privilege escalation
Remediation: Provision new privileged accounts and re-assign roles
Remediation impact: High. Need to re-provision and re-assign permissions
Learn more: Assign Azure AD roles to users
Secure registration of security info
Securing when and how users register for Azure AD multifactor Authentication and self-service password reset is possible with user actions in a Conditional Access policy. This feature is available to organizations who have enabled the combined registration.
P0: There is no CA policy targeting secure registration
P1: The CA Policy does not include device state
Threats: Account takeover
Remediation: Configure CA policy to protect registration of security info
Remediation impact: High. Need to re-provision and re-assign permissions
Learn more: Control security information registration with Conditional Access
Enable phishing resistant authentication methods
Ensure that administrators in the organization have multiple authentication methods available. Microsoft recommends phishing resistant methods such as FIDO2, Windows Hello for Business, and Certificate-Based authentication
P1: Phishing resistant methods (FIDO2, or CBA) are not configured in the tenant
P2: FIDO2 is not enabled
P2: Phishing resistant methods are not targeting all users
Threats: Phishing
Remediation: Provision and register phishing resistant methods for privileged accountes accounts
Remediation impact: Medium.Need to provision, distribute and register for administrators
Learn more: Passwordless security key sign-in
Configure a registration campaign to set up Microsoft Authenticator app
Use a registration campaign for users to register the authentication methods provided by Microsoft Authenticator app.
P1: Campaign is not configured
Threats: Password attacks
Remediation: Enable registration campagin
Remediation impact: Medium. Users will be interrupted when authenticating until they register Authenticator app
Learn more: Nudge users to set up Microsoft Authenticator - Microsoft Entra | Microsoft Learn
Use of recommended authentication methods for users
Ensure that users in the organization have multiple authentication methods available. Microsoft recommends modern authentication methods such as Authenticator App, FIDO2, Windows Hello for Business, and Certificate-Based authentication
P2: SMS/Voice auth methods are configured in the tenant
Threats: Phishing
Remediation: Remove non-recommended authentication methods so users move to better methods
Remediation impact: High. Needs user communication and campagns
Learn more: How to migrate to the Authentication methods policy
Require strong authentication for non-privileged users
Configure Azure AD to require strong authentication methods to access resources.
P0: Customer has NOT deployed a CA Policy for users that requires MFA or auth strength
Threats: Password Attacks
Remediation: Implement CA policies to require authentications strengths (recommended) or Multi-factor authentication
Remediation impact: High. Require critical mass of registration and update communications
Learn more: Require MFA for all users with Conditional Access
Enable Password Protection for on-premises accounts
Azure AD Password Protection to detect and block known weak passwords and their variants
P1: Password Protection is not enforced for On-premises Active Directory
Threats: Password Spray
Remediation: Deploy Password Protection
Remediation impact: Low
Learn more: Assign Azure AD roles to users
Enable custom list of banned passwords
Azure AD Password Protection custom banned password list prevents your users from using in their passwords that might be speciific to your organization, such as your products, trademarks, industries, local cities and towns, and local sports teams. These are case insensitive, and common character substitutions (o for 0, etc) are automatically considered.
P1: Custom list of password is not implemented
Threats: Password Spray
Remediation: Define and configure the list of banned passwords based on the context of the organization
Remediation impact: Low
Learn more: Configure custom Azure Active Directory password protection lists
Mobile Application Management enforcement
No on-premises accounts should have administrative privileges in Microsoft 365.
P1: There are no Conditional Access Policies with the control "Require App protection Policy", for iOS and Android Devices
Threats: Data Exfiltration
Remediation: Align MAM policies with Conditional Access
Remediation impact: Low
Learn more: Conditional Access - Require approved app or app protection policy
Compliant device enforcement
Configure device compliance policy with Microsoft intune and enforce at access time with Conditional Access
P1: There are no Conditional Access Policies with the control "Require compliant device" or Hybrid Azure AD Joined device.
Threats: Data Exfiltration
Remediation: Align MDM policies with Conditional Access
Remediation impact: Low
Learn more: Require compliant, hybrid joined devices, or MFA
<TenantName>
aka.ms/ztassess

## Device ☑️
[6 empty] | Legend | ☉ Not started | ✜ Planned | ▷ In progress | ✓ Completed | ⦿ Blocked | ※ Third Party | ✕ Will not pursue | ⚐ MS Roadmap | ☉ Not started (P0)
Assessment check |  | Result |  | User impact | Risk level
Enroll devices into MDM management
| 🚦 |  | Windows automatic enrollment | Moderate | Moderate
Device compliance policies to ensure devices meet minimum requirements
| 🚦 |  | Configure compliance policies for Android (AOSP) | Moderate | High
| 🚦 |  | Configure compliance policies for Android device administrator | Moderate | High
| 🚦 |  | Configure compliance policies for Android Enterprise (Fully managed and corporate owned work profile) | Moderate | High
| 🚦 |  | Configure compliance policies for Android Enterprise (Personally-owned work profile) | Moderate | High
| 🚦 |  | Compliance policies for iOS / iPadOS | Moderate | High
| 🚦 |  | Compliance policies for macOS | Moderate | High
| 🚦 |  | Compliance policies for Windows 10 and later | Moderate | High
Configure Enrollment restrictions
| 🚦 |  | Configure enrollment restrictions for Android devices | Low | High
| 🚦 |  | Configure enrollment restrictions for iOS/iPadOS devices | Low | High
| 🚦 |  | Configure enrollment restrictions for macOS devices | Low | High
| 🚦 |  | Configure enrollment restrictions for Windows devices | Low | High
Protect from data leakage on mobile devices at the application layer
| 🚦 |  | Android - Intune App Protection Policy assigned | High | High
| 🚦 |  | iOS/iPadOS - Intune App Protection Policy assigned | High | High
| 🚦 |  | Android root detection is enabled - App Protection | High | High
| 🚦 |  | iOS Jailbreak detection is enabled - App Protection | High | High
| 🚦 |  | Android root detection is enabled - Device Compliance Policy | High | High
| 🚦 |  | iOS Jailbreak detection is enabled - Device Compliance Policy | High | High
| 🚦 |  | Microsoft Defender for Endpoint is configured | High | High
| 🚦 |  | Windows - Windows Update policy is assigned | Low | High
| 🚦 |  | Windows - BitLocker is assigned | Moderate | Moderate
| 🚦 |  | Windows Hello for Business is assigned | Moderate | High
| 🚦 |  | Windows - Firewall is enabled | High | High
| 🚦 |  | macOS - Firewall is enabled | High | High
Android (AOSP) - Intune Compliance Policy assigned
Microsoft Intune Compliance Policies compare a device's security configuration and health based on rules and settings that devices must meet to be considered compliant. Corporate data and resources can be restricted based on the compliance of a managed device.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Create and assign an AOSP compliance policy.
Remediation impact: This change will have low impact on your users.
Android device administrator - Intune Compliance Policy assigned
Microsoft Intune Compliance Policies compare a device's security configuration and health based on rules and settings that devices must meet to be considered compliant. Corporate data and resources can be restricted based on the compliance of a managed device.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Create and assign an Android device administrator compliance policy.
Remediation impact: This change will have low impact on your users.
Android Enterprise - Fully Managed - Intune Compliance Policy assigned
Microsoft Intune Compliance Policies compare a device's security configuration and health based on rules and settings that devices must meet to be considered compliant. Corporate data and resources can be restricted based on the compliance of a managed device.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Create and assign an Android Enterprise compliance policy.
Remediation impact: This change will have low impact on your users.
Android Enterprise - personally owned Work Profile - Intune Compliance policy assigned
Microsoft Intune Compliance Policies compare a device's security configuration and health based on rules and settings that devices must meet to be considered compliant. Corporate data and resources can be restricted based on the compliance of a managed device.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Create and assign an Android Enterprise compliance policy.
Remediation impact: This change will have low impact on your users.
iOS/iPadOS - Intune Compliance Policy assigned
Microsoft Intune Compliance Policies compare a device's security configuration and health based on rules and settings that devices must meet to be considered compliant. Corporate data and resources can be restricted based on the compliance of a managed device.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Create and assign an iOS/iPadOS compliance policy.
Remediation impact: This change will have low impact on your users.
macOS - Intune Compliance Policy assigned
Microsoft Intune Compliance Policies compare a device's security configuration and health based on rules and settings that devices must meet to be considered compliant. Corporate data and resources can be restricted based on the compliance of a managed device.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Create and assign a macOS compliance policy.
Remediation impact: This change will have low impact on your users.
Windows 10 and later - Intune Compliance Policy assigned
Microsoft Intune Compliance Policies compare a device's security configuration and health based on rules and settings that devices must meet to be considered compliant. Corporate data and resources can be restricted based on the compliance of a managed device.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Create and assign a Windows 10 and later compliance policy.
Remediation impact: This change will have low impact on your users.
Device Zero Trust Assessment
Score
-%
Windows automatic enrollment
Windows automatic enrollment enables a device to be automatically managed by Microsoft Intune as part of the initial sign on to the device. This ensures the device is protected by the security policies defined by the organization.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Enable Windows devices to automatically enroll for management with Microsoft Intune.
Remediation impact: This change will have low impact on your users.
Learn more: Enable MDM automatic enrollment for Windows
Configure enrollment restrictions for Android devices
Device enrollment restrictions let you restrict devices from enrolling in Intune based on certain device attributes. Device attributes that can be used to block enrolling include device limit, device platform, OS version, device manufacturer and device ownership (personally-owned devices).
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Configure an enrollment restriction for Android devices.
Remediation impact: This change will have low impact on your users.
Learn more: Overview of enrollment restrictions - Microsoft Intune
Configure enrollment restrictions for iOS/iPadOS devices
Device enrollment restrictions let you restrict devices from enrolling in Intune based on certain device attributes. Device attributes that can be used to block enrolling include device limit, device platform, OS version, device manufacturer and device ownership (personally-owned devices).
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Configure an enrollment restriction for iOS devices.
Remediation impact: This change will have low impact on your users.
Learn more: Overview of enrollment restrictions - Microsoft Intune
Configure enrollment restrictions for macOS devices
Device enrollment restrictions let you restrict devices from enrolling in Intune based on certain device attributes. Device attributes that can be used to block enrolling include device limit, device platform, OS version, device manufacturer and device ownership (personally-owned devices).
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Configure an enrollment restriction for macOS devices.
Remediation impact: This change will have low impact on your users.
Learn more: Overview of enrollment restrictions - Microsoft Intune
Configure enrollment restrictions for Windows devices
Device enrollment restrictions let you restrict devices from enrolling in Intune based on certain device attributes. Device attributes that can be used to block enrolling include device limit, device platform, OS version, device manufacturer and device ownership (personally-owned devices).
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Configure an enrollment restriction for Windows devices.
Remediation impact: This change will have low impact on your users.
Learn more: Overview of enrollment restrictions - Microsoft Intune
Android - Intune App Protection Policy assigned
Microsoft Intune App Protection Policies provide data security and data loss prevention for iOS and Android apps.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Clicking the manage button below will take you to the App protection policies blade of the Microsoft Intune console where you can create an App Protection Policy.
Remediation impact: This change will have low impact on your users.
iOS/iPadOS - Intune App Protection Policy assigned
Microsoft Intune App Protection Policies provide data security and data loss prevention for iOS and Android apps.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Clicking the manage button below will take you to the App protection policies blade of the Microsoft Intune console where you can create an App Protection Policy.
Remediation impact: This change will have low impact on your users.
Android root detection is enabled - App Protection
Microsoft Intune App Protection Policies and Compliance Policies both have the ability to enforce that devices not be rooted in order to get access to corporate data.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Enable Android root detection in Microsoft Intune App Protection Policy.
Remediation impact: This change will have low impact on your users.
iOS Jailbreak detection is enabled - App Protection
Microsoft Intune App Protection Policies and Compliance Policies both have the ability to enforce that devices not be jailbroken in order to get access to corporate data.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Enable Jailbreak Detection in Microsoft Intune App Protection Policy.
Remediation impact: This change will have low impact on your users.
Android root detection is enabled - Device Compliance Policy
Microsoft Intune App Protection Policies and Compliance Policies both have the ability to enforce that devices not be rooted in order to get access to corporate data.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Enable Android root detection in Microsoft Intune Compliance Policy. Browse to the Device compliance blade of the Microsoft Intune console where you can create and assign a Compliance Policy.
Remediation impact: This change will have low impact on your users.
iOS Jailbreak detection is enabled - Device Compliance Policy
Microsoft Intune App Protection Policies and Compliance Policies both have the ability to enforce that devices not be jailbroken in order to get access to corporate data.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Enable Jailbreak Detection in Microsoft Intune App Protection Policy. Browse to the Device compliance blade of the Microsoft Intune console where you can create and assign a Compliance Policy.
Remediation impact: This change will have low impact on your users.
Microsoft Defender for Endpoint is configured
Microsoft Defender for Endpoint provides visibility into your organizations security posture and provides recommendations to improve it.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Enable Microsoft Defender for Endpoint integration into Microsoft Intune and then apply a device compliance policy based on device risk. Browse to the Device Compliance blade of the Microsoft Intune console where you can configure the Windows Defender policy.
Remediation impact: This change will have low impact on your users.
Windows - Windows Update policy is assigned
Configure Windows Updates for Business to simplify the update management experience for users and ensure that devices are automatically updated to meet the required compliance level.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Enable Windows Updates for Business policy in Microsoft Intune.
Remediation impact: This change will have low impact on your users.
Windows - BitLocker is assigned
Ensure devices are encrypted using BitLocker to ensure you protect against the threats of data theft or exposure from lost, stolen, or inappropriately decommissioned computers.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Enable BitLocker device encryption policy in Microsoft Intune.
Remediation impact: This change will have low impact on your users.
Windows Hello for Business is assigned
To allow users an alternative sign-in method that replaces a password, such as PIN, biometric authentication, or fingerprint reader, enable Windows Hello for Business on users' Windows 10 and Windows 11 devices.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Enable Windows Hello for Business in Microsoft Intune.
Remediation impact: This change will have low impact on your users.
Windows - Firewall is enabled
Use the endpoint security Firewall policy in Intune to configure a devices built-in firewall for devices that run Windows devices.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Enable a firewall policy for Windows devices in Microsoft Intune.
Remediation impact: This change will have low impact on your users.
macOS - Firewall is enabled
Use the endpoint security Firewall policy in Intune to configure a devices built-in firewall for devices that run macOS devices.
Threats: Data Exfiltration, Data Deletion, Password Cracking, Data Spillage
Remediation: Enable a firewall policy for macOS devices in Microsoft Intune.
Remediation impact: This change will have low impact on your users.
<TenantName>
aka.ms/ztassess